## Deliverables Status
Nifty 100 Financial Intelligence Platform — Deliverables Status (Day 45 Sign-Off)
Project Release Sign-Off Status: ALL 23 DELIVERABLES COMPLETED ¦ ALL 20 ACCEPTANCE GATES PASSED (RELEASE-PASS-DAY45)
ID | Sprint | Deliverable | Location | Status | Verification & Artifact Details
D-01 | Sprint 1 | nifty100.db | data/nifty100.db | Done | SQLite DB with 13 tables & composite B-tree indexes
D-02 | Sprint 1 | load_audit.csv | output/load_audit.csv | Done | Log of rows ingested across P&L, BS, Cash Flow
D-03 | Sprint 1 | validation_failures.csv | output/validation_failures.csv | Done | Data Quality audit failure report (16 DQ rules)
D-04 | Sprint 1 | exploratory_queries.sql | notebooks/exploratory_queries.sql | Done | SQL queries for trend & sector exploratory analysis
D-05 | Sprint 2 | financial_ratios table | data/nifty100.db -> financial_ratios | Done | 1,164 ratio records (ROE, ROCE, D/E, OPM, NPM, etc.)
D-06 | Sprint 2 | capital_allocation.csv | output/capital_allocation.csv | Done | 8 capital allocation patterns classified across 92 companies
D-07 | Sprint 3 | screener_output.xlsx | output/screener_output.xlsx | Done | Winsorized, composite-weighted multi-preset screener export
D-08 | Sprint 3 | screener_config.yaml | config/screener_config.yaml | Done | Screener YAML config with weights, ranges & rules
D-09 | Sprint 3 | peer_comparison.xlsx | output/peer_comparison.xlsx | Done | Peer percentile matrix across 11 sector peer groups
D-10 | Sprint 3 | 92 Radar Charts | reports/radar_charts/ | Done | 92 high-res 8-axis PNG radar charts
D-11 | Sprint 4 | Streamlit Dashboard (8 Screens) | src/dashboard/app.py | Done | Interactive 8-screen Streamlit web dashboard
D-12 | Sprint 4 | valuation_summary.xlsx | output/valuation_summary.xlsx | Done | Multi-year valuation multiples (P/E, P/B, EV/EBITDA, etc.)
D-13 | Sprint 5 | cashflow_intelligence.xlsx | output/cashflow_intelligence.xlsx | Done | FCF CAGR, CapEx intensity & CFO quality metrics
D-14 | Sprint 5 | pros_cons_generated.csv | output/pros_cons_generated.csv | Done | NLP-extracted key strengths and risks per company
D-15 | Sprint 5 | analysis_parsed.csv | output/analysis_parsed.csv | Done | Parsed text analysis metadata
D-16 | Sprint 5 | 92 Company Tearsheets | reports/tearsheets/ | Done | 92 2-page publication tearsheet PDFs (>= 30 KB each)
D-17 | Sprint 5 | 11 Sector Reports | reports/sector/ | Done | 11 broad sector comparative PDF reports
D-18 | Sprint 5 | Portfolio Summary PDF | reports/portfolio/ | Done | 92-company portfolio aggregate PDF summary
D-19 | Sprint 6 | cluster_labels.csv | output/cluster_labels.csv | Done | KMeans (k=5) archetype cluster assignments
D-20 | Sprint 6 | FastAPI Server (16 Endpoints) | src/api/main.py | Done | 16 REST endpoints, OpenAPI 3.0 & Postman collection
D-21 | Sprint 6 | pytest_report.html | reports/pytest_report.html | Done | Self-contained HTML report (166 passing tests, 0 failures)
D-22 | Sprint 6 | analyst_guide.pdf | docs/analyst_guide.pdf | Done | 11-page User & Developer Guide PDF
D-23 | Sprint 6 | acceptance_checklist.pdf | docs/acceptance_checklist.pdf | Done | Verified sign-off PDF covering all 20 Acceptance Gates